SYLLABUS

- Data about the program of study

| 1.1 | Institution | The Technical University of Cluj-Napoca |
| --- | --- | --- |
| 1.2 | Faculty | Faculty of Civil Engineering |
| 1.3 | Department | Buildings and Management |
| 1.4 | Field of study | Civil Engineering |
| 1.5 | Cycle of study | Master of Science |
| 1.6 | Program of study/Qualification | Artificial Intelligence in Construction Engineering and Management |
| 1.7 | Form of education | Full time |
| 1.8 | Subject code | 17.05 |

- Data about the subject

| 2.1 | Subject name |  |  |  | Integrated Project Management in Constructions |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 2.2 | Subject area |  |  |  | Civil Engineering |  |  |  |
| 2.3 | Course responsible/lecturer |  |  |  | Conf. dr. ing. dr. ec. Dorin MAIER dorin.maier@ccm.utcluj.ro |  |  |  |
| 2.4 | Teachers in charge of seminars |  |  |  | Conf. dr. ing. dr. ec. Dorin MAIER dorin.maier@ccm.utcluj.ro |  |  |  |
| 2.5 Year of study |  | II | 2.6 Semester | I | 2.7 Assessment | C | 2.8 Subject category | DS/DO |

- Estimated total time

| 3.1 Number of hours per week |  | 3 | 3.2 of which, course: |  |  | 2 | 3.3 applications: | 1 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 3.4 Total hours in the curriculum |  | 42 | 3.5 of which, course: |  |  | 28 | 3.6 applications: | 14 |
| Individual study |  |  |  |  |  |  |  | hours |
| Manual, lecture material and notes, bibliography |  |  |  |  |  |  |  | 20 |
| Supplementary study in the library, online and in the field |  |  |  |  |  |  |  | 20 |
| Preparation for seminars/laboratory works, homework, reports, portfolios, essays |  |  |  |  |  |  |  | 14 |
| Tutoring |  |  |  |  |  |  |  | 2 |
| Exams and tests |  |  |  |  |  |  |  | 2 |
| Other activities |  |  |  |  |  |  |  |  |
| 3.7 | Total hours of individual study |  |  | 58 |
| 3.8 | Total hours per semester |  |  | 100 |
| 3.9 | Number of credit points |  |  | 4 |

- Pre-requisites (where appropriate)

| 4.1 | Curriculum |  |
| --- | --- | --- |
| 4.2 | Competence |  |

- Requirements (where appropriate)

| 5.1 | For the course | Classroom with blackboard, video-projector. Students will participate to courses and applications without opened mobile phones. Moreover, phone-calls will not be tolerated during courses, nore leaving the class for answering personal phone-calls. |
| --- | --- | --- |
| 5.2 | For the applications | Classroom with computers, software packages (for estimations and planning the construction works). The timeline for delivering the application project is mutually established with the students. For late delivery of the application project, the students will be punished by 1 point per day of delay. |

- Specific competences

| Professional competences | Understanding and applying advanced integrated management principles, adapting them to the specific requirements of modern, technology-driven, and sustainable projects in the construction industry. Leading and optimizing construction execution processes using Common Data Environments (CDE) and BIM models for resource planning, monitoring, and control. Conducting and interpreting Life Cycle Assessments (LCA) to substantiate technical and economic decisions in the selection of materials, equipment, and execution technologies. Integrating sustainable innovation tactics and circular economy principles into all development and management phases of a civil engineering project. Utilizing critical reasoning and data analysis tools to optimize decision-making processes, reduce financial risks, and ensure contractual performance. Implementing Green Human Resource Management (Green HRM) practices to develop high-performing, motivated project teams aligned with sustainability standards. Integrated management of budgets and schedules through digital platforms, directly correlating financial performance indicators with carbon footprint feasibility analyses |
| --- | --- |
| Cross competences | Rigorously applying the principles, norms, and values of professional ethics, assuming responsible leadership for managerial decisions with technical, economic, and environmental impacts on the project. Identifying roles and efficiently coordinating multidisciplinary teams, applying advanced techniques for negotiation, conflict management, and collaborative communication in digital environments. Actively promoting innovation and sustainable practices in the professional work environment, positively influencing the organizational culture on site and in relationships with business partners. Autonomously identifying opportunities for continuous life-long learning and capitalizing on complex professional information (e-learning platforms, specialized software, scientific databases) for rapid adaptation to innovations in civil engineering. |

- Discipline objectives (as results from the key competences gained)

| 7.1 | General objective | Understanding the essential role of integrated construction project management in the current context of digitalization, circular economy, and sustainable innovation. Developing the capacity to implement advanced methods for integrating project stages, utilizing technological platforms and approaches based on the building's life cycle assessment. Training students for applied research and individual study in order to solve complex managerial challenges on modern construction sites. |
| --- | --- | --- |
| 7.2 | Specific objectives | Ability to substantiate and analyze the success of a project by integrating classic performance indicators with carbon-cost feasibility studies and preliminary life cycle assessments (LCA). Ability to form, coordinate, and motivate a multidisciplinary project team by applying green human resource management strategies. Ability to manage communication and resolve operational or contractual conflicts in collaborative and digitalized work environments. |

- Contents

| 8.1. Lecture (syllabus) | Teaching methods | Notes |
| --- | --- | --- |
| - Introduction to integrated construction project management: The evolution from classic approaches to digital ecosystems and technology-assisted management. | Presentation, discussions | Video-projector |
| - Life Cycle Assessment (LCA): Fundamental principles, methodologies, and the use of LCA as a managerial tool in civil engineering. |  |  |
| - Sustainable innovation and circular economy: Integrating the principles of waste reduction, reuse, and structural optimization in the decision-making phases of the project. |  |  |
| - Carbon-cost feasibility: Conducting integrated feasibility studies to assess financial costs in correlation with carbon emission taxation for the real estate developer market. |  |  |
| - Project initiation and Common Data Environment (CDE): Defining the scope, objectives, and establishing the collaborative data architecture. |  |  |
| - Green Human Resource Management (Green HRM): Strategies for team building, defining responsibilities, and promoting sustainability-oriented behavior on the construction site. |  |  |
| - Time and resource planning: Modern methods for duration estimation and the integration of 4D planning for visualizing execution sequences. |  |  |
| - Cost and procurement management: Traceability of low-impact materials (e.g., hybrid solutions, cross-laminated timber) and supply chain optimization. |  |  |
| - Quality and execution management: Implementing digitally assisted quality inspections and monitoring the physical progress of the works. |  |  |
| - Communication and conflict management: Negotiation and resolution techniques for technical or contractual bottlenecks in multidisciplinary teams and online environments. |  |  |
| - Monitoring and control (I): Using performance management systems (Earned Value Management) adapted for technical-economic and environmental criteria. |  |  |
| - Monitoring and control (II): Predictive risk analysis, identifying deviations, and implementing rapid corrective measures. |  |  |
| - Subcontractor and Claim Management: Practical approaches for ensuring performance and resolving disputes on the construction site. |  |  |
| - Project closure and experience capitalization: Handover procedures, delivering as-built digital documentation, and post-execution evaluation. |  |  |
| Bibliography Note de curs Project Management Institute (2021). A Guide to the Project Management Body of Knowledge (PMBOK® Guide) – Seventh Edition. PMI, USA. Fewings, P., Henjewele, C. (2019). Construction Project Management: An Integrated Approach, 3rd Edition, Routledge, USA. Kineber, A. F., Othman, I., Oke, A. E., Chileshe, N., & Zayed, T. (2023). Value Management and Sustainable Construction. Routledge. Oesterreich, T. D., & Teuteberg, F. (2016). Understanding the implications of digitization and automation in the context of Industry 4.0: A triangulation approach and elements of a research agenda for the construction industry. Computers in Industry. ISO 21502:2020 – Project, program and portfolio management — Guidance on project management. ISO 19650-1 & 2:2018 – Organization and digitization of information about buildings and civil engineering works, including building information modelling (BIM) — Information management using building information modelling. EN 15978:2011 (or actualized version) – Sustainability of construction works Assessment of environmental performance of buildings — Calculation method. Directive (EU) 2024/1275 (EPBD recast) – On the energy performance of buildings. |  |  |

| 8.2. Applications/Seminars | Teaching methods | Notes |
| --- | --- | --- |
| - Presenting the project theme and initiation: Defining the hypotheses, configuring the Work Breakdown Structure (WBS), and the initial allocation of team roles. | Presentation, applications, softs | Video-projector |
| - Developing the preliminary carbon-cost study: Evaluating two competing structural/architectural scenarios based on financial indicators and the estimated carbon footprint. |  |  |
| - Life Cycle Assessment (LCA): Applying preliminary calculation tools for the environmental impact generated by the main materials proposed for execution. |  |  |
| - Human resources matrix and Green HRM: Creating the project's organizational chart and defining individual performance indicators related to the sustainable management of the construction site. |  |  |
| - Time-cost planning integration: Developing the optimized Gantt chart and correlating it with the allocated budget, identifying the critical path. |  |  |
| - Risk management: Identifying operational and financial risks by using decision trees and probability-impact matrices; establishing the response plan. |  |  |
| - Project delivery and evaluation: Defending the complete portfolio and justifying the managerial decisions adopted during the simulation. |  |  |
| Bibliography FIDIC Conditions of Contract – Red Book (Construction) and Yellow Book (Plant and Design-Build). EU Taxonomy for Sustainable Activities – Technical screening criteria for construction and real estate activities. AACE International – Recommended Practice No. 18R-97: Cost Estimate Classification System - As Applied in Engineering, Procurement, and Construction for the Process Industries. |  |  |

- Bridging course contents with the expectations of the representatives of the community, professional associations and employers in the field

The course content is directly correlated with the demands of the European market and major real estate developers regarding the digital and ecological transition of the construction industry. The acquired competences prepare future managers and consultants to integrate carbon-cost feasibility analyses, Life Cycle Assessments (LCA), and sustainable innovation into the decision-making processes of modern organizations.

- Evaluation

| Activity type | 10.1 Assessment criteria |  | 10.2 Assessment methods | 10.3 Weight in the final grade |  |
| --- | --- | --- | --- | --- | --- |
| 10.4 Course | Solving a practical case study. Face-to-face exam topics with the examiner. |  | Written test: 1 hour Oral exam | 70 % |  |
| 10.5 Applications | Delivery of the project. |  | Project evaluation | 30 % |  |
| Obs: In exceptional situations, the assessment activity can take place online. |  |  |  |  |  |
| 10.6 Minimum standard of performance a) Eligibility condition for taking the exam: attendance at a minimum of 12 laboratory sessions and submission of assignments on time. Project grade (to be entered in the electronic grading book): (P) min. 5 (five). (b) Theory grade (T): min. 5 (five). Grade calculation formula: $E = 0.7(T) + 0.3(P)$ Passing / credit obtaining condition: $E \ge 5$, if $T \ge 5$ and $P \ge 5$. OBS: When determining the final grade, the student's involvement throughout the semester will also be taken into account: participation in courses, debates, scientific sessions, attendance, etc. |  |  |  |  |  |

| Date of filling in: |  | Title Surname Name | Signature |
| --- | --- | --- | --- |
| 22.06.2026 | Lecturer | Assoc. Prof. PhD. Eng. PhD Ec. Dorin MAIER |  |
|  | Teachers in charge of application | Assoc. Prof. PhD. Eng. PhD Ec. Dorin MAIER |  |

| Date of approval in the department 23.06.2026 | Head of department Assoc. Prof. PhD. Eng. Claudiu ACIU |
| --- | --- |
| Date of approval in the faculty 24.06.2026 | Dean Prof. PhD. Eng. Daniela MANEA |